### MYCM Report for 2022-2023

# Japan East Region

Report Date: 17 Feb　2023

Sato Shigeyoshi, RD of Japan East Region 2022-2023

### 1. Reports on your progress toward your goals (activities from  November　2022 to January　2023)

(1) CS and YSA projects

(a). Covid-19 less frequently, so activities such as charity runs, charity concerts, river rafting, etc. could be carried out.

(b)Implemented World Clean-up Day in 17 December.

(ｃ) To activate CS activities, is compiling a pro bono list of club members (professions/expertise).

(2) Membership development projects

(a) The EMC Committee was able to implement an action plan for membership growth (July to December).

A Team: Worked with the YMCA to promote Y's activities in the YMCA's magazine.

Team B: Same as before, but approached general acquaintances and friends.

Team C: Teams that have established new clubs are currently working on their activities.

(b) 100-day membership campaign from 1September 9 December. Analyze the current membership numbers (age groups, etc.), inform everyone in the district of the current situation and raise awareness of membership growth. (Completed in December)

(c) Establishment of new clubs 3 September 2022 Charter “Kofu Yamanami Club “11 members

(Established mainly with young members)

(d) +4members against a target of 60.

(3) International and exchange activities

(a) Promoted the BF stamp collection to be actively implemented.

(b) Conducted in the Director's newsletter to make donations more visible and to deepen understanding of donations.

(c) Preparations were underway for festive events such as the YMI 100th anniversary and the 25th anniversary of the establishment of the East West Japan District. Meetings 3 times month.

(4) Youth projects

(a) Participation of 5youth in IYC (Chiang Mai, Thailand). (4-9 Sept).

The meeting was meaningful for young people as they deepened exchanges with overseas youth.

(b) Youth Action, a joint activity of the YMCA and the East and West Wards, supporting youth teams on the theme of the SDGs. Six teams supported in the East Japan Wards are currently active. Three teams to present at the East-West Japan Exchange on February 5.

(c) 34th YVLF. 30youth, 10 supporting YMCAs and 20 Y's, 60 participants in total. 30 September - 2 October. Supported youth exchanges.

(d) Provided financial support and advice on activities for both IYC, Youth Action and YVLF.

### 2. Reports on your plans (February to June)

(1) CS and YSA projects

(a) Promote CS and YSA activities in 59 clubs.

Plan one activity (utilizing grants) that takes advantage of the benefits of incorporation (one with the YMCA in Kofu).

(b) Progress is being made to complete the pro bono list..

(2) Membership development projects

(a) Continue to promote the activities of the Membership Development A, B, and C Teams; promote a 92-day membership campaign (EMC seminars for each districe) from March 1 to the end of May.

(b) Strengthen extension activities and establish new clubs, with a target of two clubs.

(c) Promote membership growth, aiming for a net increase of 60 members by the end of the year.

(3) International and exchange activities

(a) Promote participation in YMI's 100th anniversary convention.

(b) Promote participation in the East West Japan District's 25th anniversary social event.

Conducted on February 4 and 5, 2023 (430 participants, of which 130 participated in JER)

(c) Achieve the donation target.

(4) Youth projects

(a) Supporting Youth Action (SDGs) teams (plan to present in 3 June at JER Convention)

(b) OFY (Open Forum Y) to be held from April to May 2023

(c) Continue to promote establishing youth clubs (target 3 clubs).

(d) Targeted financial support and grant applications for Youth Action Teams

### 3. Challenges you feel you are facing in carrying out the assignment (if any)

(a) Expected decrease in donations due to the impact of the weak yen

(b) Lack of activity due to the current corona (not returning to its original vitality)

### 4. What can the Area help you with (if any)

I would like all costs related to hosting BF Ambassadors(transportation, Hotel expense) to be borne by YMI or APA.

### 5. Items you would like to see discussed at ACM (if any)

### Reduced submittals and meetings of less than 2 hours（Zoom meeting）

### 6. Other comments (if any)